## Sheet1
Church Buildings Projects - Simple Flowchart
Sections
A: Basics
B:Vision
C: Team including procurement and evaluation |  |  | Produced as part of the National Lottery Heritage Fund Inspired Ideas funding stream.
D: Community Engagement
E: Evidence
F: DAC Visit and Faculty Process
G: Fundraising and grants
H: Project development
I: Project delivery
J: End of project and evaluation
K: Next steps
Section A - Basics
Stage | Simple | Slightly more detail
A1 | Check on-going tasks |  | Additional detail / resources
A1a | Maintenance | Maintenance plan in place, budget for maintenance works, minor works carried out in good time, weekly and monthly checks.
A1b | Quinquennial Inspection (QI) | Required to be carried out every 5 years by an architect or surveyor, this will give an idea of the condition of the building, repairs required and the urgency. | Work with local contractors to clear rainwater goods twice a year, check gutters during rain, look at roof regularly. SPAB have useful resources: https://www.spab.org.uk/campaigning/maintenance-co-operatives-project/mcp-fim-resources
A1c | Terrier and Inventory | The records of church buildings, land and contents required to be kept by the churchwardens. | You can work with the architect who carried out the previous QI or choose another one. Ask the Church Buildings Team about procurement. Look at the Quinquennial Inspection Guidance Note. Action the repairs. Write what has taken place in the Log Book.
A2 | Kerb appeal | Regularly review what the church building looks like from the roadside. Would you want to visit? | Review at least once a year, add any new items, make a note of any items sold or permanently removed. Photographs are useful to identify items. Keep a copy off site, in case of disaster.
A3 | Open and Welcome
A3a |  | Open the church door regularly and make sure visitors feel welcome. | Paths clear, noticeboard up to date, easy to use gates, signage.
A3b |  |  | Many people will just pop in for the peaceful atmosphere and beautiful space. Is the church clean and tidy with information about the building and the faith?
Section B - Vision
Stage | Simple | Slightly more detail
B1 | Develop the vision |  | Additional detail / resources
B1a | Why now? | Do you have to carry this project out now?
B1b | How are you called to be church in this place? | How are you being called to be church in this place, now, 5 years, 10 years? | How do you know? What has sparked the idea?
B1c | What is already happening in church and wider community? | Map what is happening in church building and other places in settlement. | Local data will be available via the Welsh Government/County Council
B1d | Who have you asked? | Don't keep the idea to yourself and assume everyone else will go along with it! | Think about groups, schools, spaces, your wider networks. Are there any gaps? Are there any pinchpoints?
B1e | What is already here? | Think of spaces in and around church and infrastructure. | Ask for ideas and input from PCC, Congregation and Wider Community
B1f | Have you considered fully all the possibilities? | You need to be able to show you have thought everything through. | Will the infrastructure need to be upgraded or installed? Water, electricity, gas, drainage. How long will this take?
The vision needs to be more that the roof needs fixing or we need a toilet and servery; include why you are doing this. Can you sell the vision to others including the wider community and funders?
Section C - Team including procurement and evaluation
Stage | Simple | Slightly more detail
C1 | Gathering a team |  | Additional detail / resources
C1a | Who do you need? | Chair, Secretary and Treasurer as a minimum but project management, fundraising, IT and communications useful.
C1b | Who have you got already? | Carry out a skills audit of PCC, wider congregation and wider community. | It is easier for 10 people to find a bit of spare time than 2 people to carry the whole project.
C1c | How will the group operate? | Organisation set up, bank account, consitution, reporting lines, meetings, who does what.
C1d | Volunteer hours count | Keep a record of hours given to the project. | How the group is run is crucial to the success of the project and to show external funders that the group is professional in outlook.
C2 | Procurement: how to find appropriate professionals to work with | For all but the most basic works, you will need appropriate professional support. It is wise to ensure procurement process is followed particularly for larger projects, so that you know you are getting value for money. The process needs to be fair and open. | Volunteer hours can be counted as in kind contribution to the project. NLHF volunteer rate count £20 per hour given.
C2a | Write a brief | Write a brief outlining what works you want the architect to do for this and future projects (include Quinquennial Inspection and associated works if appropriate). | Unless you have evidence that you procured your QI architect, start again. This does not stop your QI architect from applying. If the fees will be more than £10,000, you need to go through a formal procurement process to appoint your architect / surveyor. Some funders, including the National Lottery Heritage Fund require procurement to have taken place before grants can be given.
C2b | Advertise for interest | Advertising via the Churchcare Website is free. | The Church Buildings Team can help you with this.
C2c | Assess responses | Ask a shortlist to tender. | Those who are interested send in answers to a pre qualification questionnaire.
C2d | Interview | Invite a selection to interview depending on tender responses. | Compare responses to the pre qualification questionnaire and ask those who you would like to interview, to submit a tender for the work.
C2e | Appoint architect / surveyor | With the MAC's agreement, appoint the successful candidate. | Try and shortlist at least three people. Meeting them in person, you soon know if you can work with them. Use the same questions for each interview. Ensure that any contract is clear and includes details of what fees will be due for what work.
C3 | Friends Groups
C3a | Set up a Friends Group if appropriate | Friends Groups can include people who are not part of the worshipping community but who want to help look after the building or run fundraising events.
C3b | Consider different types | Three main models of Friends Schemes: Sub committee of the PCC / Separate Organisation either Independent Charity (Charitable unincorporated association or Charitable Incorporated Organisation (CIO). | Further resources can be found here: https://www.parishresources.org.uk/friends-schemes/ and here: https://www.nationalchurchestrust.org/get-support/buildings-maintenance/friends-group
C3c | Governance | Governance and communication crucial. | Speak with others who run Friends Groups and consider the purposes for which the Friends Group is being set up.
C4 | Evaluation embedded from the start | Gather data and feedback as you go. Plan what you need to evaluate and by when. | MAC still has control and legal responsibilities for certain matters.
Do not leave this to the end of the project as you will not be able to see the impact of outcomes as you go along.
Section D - Community Engagement
Stage | Simple | Slightly more detail
D1 | Information Gathering |  | Additional detail / resources
D1a | What already happens? | List the events (both regular and occassional), the community spaces and places and who runs them.
D1b | Where are the information sources in your village? | How does news get shared? Noticeboard, website, social media, school gate, post office queue, parish or village magazine. | Are some spaces full? Is the village hall always booked? Is the church the only community space? Look for gaps and overlaps.
D1c | Event questions – what else would you like to happen here? | Ask the wider community and visitors what they would like to see happen in the church. | Do not rely on one source of information sharing. Try digital, paper and in person if possible. That way more will hear about what is going on.
D1d | How can you use your space to host other community events? | Have a look at the church space both inside and out. What adaptations and / or equipment would be needed. Is there something you have always wanted to try and never have? What is stopping you? | Do not assume that you know the answers. This may help identify gaps in provision.
D1e | Keep information up to date | Keep the momentum going by reporting what is happening throughout the project planning. | Adaptations may require consent. What does your community need, based on your research and feedback from others?
D1f | Attend local events – fetes / village fairs / agricultural shows – engage in conversations | Local events are a great place to raise the profile of what you are trying to do, to gather opinions and to engage with people. They also help you to weave the church into the tapestry of the wider community. | Also keep your regular information (service times, regular events) up to date and look at whether your information sources look up to date or tired.
D1g | Never underestimate the power of tea and cake! | People know what to do with tea and cake. You can then engage with them about what is happening. | Be approachable, be prepared to chat and to listen.
Section E - Evidence
Stage | Simple | Slightly more detail | Additional detail / resources
E1 | Show what you know (or have found out)
E1a | Why do you need to do your project? | You need to be able to back your idea up with evidence. Who will benefit? | At fundraising stage, you will need to justify why you are wanting to do this. Just saying we want to fix the roof or install facilities will not be enough.
E1b | Is it being done elsewhere? | Are you the best group to deliver this? Is something the same or similar being delivered locally? | There are only so many lunch clubs that can be sustainable. Can you volunteer to help at other projects instead?
E1c | Who have you asked? | MAC, Congregation, Wider Community, other community groups and stakeholders, schools etc. | Showing that you have asked a wide range of people will demonstrate to funders that you have wider support. You may need to adapt your project as a result of feedback, but that shows you are listening and adapting accordingly.
E1d | Research including Index of Multiple Deprivation | Depending on the type of project, information on where your parish is on the Index of Multiple Deprivation can be useful along with population figures. | https://www.gov.wales/welsh-index-multiple-deprivation
E2 | Test the research
E2a | Numbers at events – show growth if possible | Keep a record of events and the number of people who attend. If it is a repeat event it is good to show a growth in numbers if possible. | Post pandemic, attendance numbers at events are lower but there is also a need to overcome social isolation. Start small and build from there.
E2b | Audits – accessibility / Open and welcome / Kerb appeal | Take a hard look at your church building, your welcome whether you are in the building or not and your kerb appeal - would you want to come in if visiting for the first time? | A Welcome Audit is available from the Church Buildings Team.
E2c | How have you reached your vision? | Gather all your evidence together and review. How has this informed and altered your original idea? | Reflect on what has changed. Put together a clear paragraph or two to summarise your vision.
Secton F - DAC Visit and Faculty Process
Stage | Simple | Slightly more detail
F1 | Before applying |  | Additional detail / resources
F1a | Ask for opinion early before you have formal plans drawn up | This is vital to the success of the project. The DAC has a wealth of experience and can guide you from early project development.
F1b | Site visits if required | A DAC Visit can help clarify the project vision. The DAC consists of a variety of volunteer experts who have seen many church development projects. | Contact Martyn Jones, DAC Secretary
F1c | Statement of Significance | This document is required to describe what is significant about the church building. | Contact Martyn Jones for advice.
F1d | Statement of Need | This document is required to justify why the building needs to be changed and the impact the changes will have on the significance. | Guidance notes are available here: https://faculty.churchinwales.org.uk/Data/Sites/3/media/guidance-notes/writing_sos_for_ofs_v1.pdf
F2 | Formal application |  | See above for guidance note link.
F2a | Ask for advice when to submit for formal faculty | DAC meetings take place 9 times a year and the agenda closes a fortnight beforehand.
F2b | Can take time to get faculty following the DAC meeting – further process | The DAC can only advise the Chancellor; they do not make the final decision. | All faculty applications are made via the online faculty system https://faculty.churchinwales.org.uk/
Anytime! | If in doubt, contact DAC Officers, who are happy to guide and help | Please ask - that is what we are here for to guide you through the process! | There is a further process after a matter has left the DAC, as it is then passed on to the Diocesan Registrar for a decision by the Chancellor.
Section G - Fundraising and grants
Stage | Simple | Slightly more detail | Additional detail / resources
G1a | Read all the guidance notes – twice | Each funder will want slightly different things. Some may not fund religion but will fund community. | Watch this video from the Diocese of Lincoln about filling in grant applications forms.https://youtu.be/ZNjMInfwEGU
G1b | Work out a fundraising strategy – who are you applying to and when? | Grant funders tend not to fund works that have already started and will not hold a deadline for you. Grants also have to be spent within a certain time. | See also Charity Excellence Framework for searchable funding finder. https://www.charityexcellence.co.uk/
G1c | Give yourself enough time to write your application bids | Each form is slightly different so be wary of cutting and pasting.
G1d | Get someone not connected to the bid to read your application | Do they understand your vision, your language, the point of the application?
G1e | Be specific - what, why, when, how, where, who | Waffle will not get you a grant - it may get you rejected. Assume that your funder knows nothing about who you are or where your project is. | Don't make things up - you will be found out!
G1f | Get you finances right on paper – almost more important than the words | If you cannot add up and understand the costings of your project, this will be obvious to a funder, who will not entrust their money with you. | Don't forget to include a contingency.
G1g | Think of other fundraising opportunities. Raise money for church fabric not for the church roof. Can the MAC put any money in? | Digital giving, QR code, concerts, fetes, coffee mornings, sponsored slate / chair / minute, plant sales, Hymns and Pimms, flower festival, to name but a few. | Ask other churches what has worked for them.
Section H - Project development
Stage | Simple | Slightly more detail | Additional detail / resources
H1a | Test your ideas | Investigate the fabric of the church more closely or test an event. | Finding funding for feasibility studies can be a struggle but the more information you have before the main project starts, the more successful it will be.
H1b | Run some events | Test the logistics, work out your communications, what are you missing?
H1c | Recruit volunteers | You may need more people to help - ask your wider community and other networks.
H1d | Keep gathering your evidence | Keep a note of what you find from investigations or test events as this shows funders you have thought the bigger project through carefully. | If you have to change the project as a result of this project development stage, funders are more likely to be supportive if they can see why.
H1e | Feasibility studies | Again, this shows potential funders that you have thought the project through.
H1f | On-going sustainability | This is not just about environmental impact but also the people needed to run events, being able to adapt to changing circumstances (not just a global pandemic) but local developments and changes in key personnel for instance. | What will your project look like in 2 years, 5 years, 10 years?
Section I - Project delivery
Stage | Simple | Slightly more detail | Additional detail / resources
I | Onsite
I1a | Cash flow – learn about Gantt charts! | A gantt chart, which shows tasks against a time line with projected costs, will make the project proceed more smoothly. | Keep an eye on the cash flow and remember that many funders pay in arrears once work has taken place.
I1b | Building works on site – mostly architect led but be aware of Health and Safety | Are you going to have to close the church? How much notice is needed for weddings and funerals?
I2 | On-going Communication
I2a | Keep your community up to date with what is happening | Communication is critical especially if there is going to be disruption. Use social media, website and church magazine. | Can you share photographs of usually unseen parts of the church as they are repaired or altered?
I2b | Community days if possible with hard hat tours | Getting to see the works on site is a great educational experience - just make sure the risk assessment is in place. | Can you also talk with the specialist contractors about the work they are doing, which can be a once in a generation event.
I3 | On-going Administration
I3a | Keep all invoices / receipts | You will need these to show what you have spent and claim your grant funding.
I3b | VAT reclaim via Listed Places of Worship Grant Scheme | Get your first application in early as can take time to process. Once you have accrued £1000 VAT - claim it back within a year. | Listed Places of Worship Grant Scheme: https://www.lpwscheme.org.uk/
Section J - End of project and evaluation
Stage | Simple | Slightly more detail | Additional detail / resources
J1 | Evaluation
J1a | How did it go? Any unexpected developments? | Evaluation of the project will be easier if you have thought about it from the beginning. What have you learnt and what would you differently? | Some funders, such as the National Lottery Heritage Fund, will expect you to budget for evaluation.
J1b | Did you achieve your project outcomes? How has the funding made a difference? | Reflect on the project journey. Has the project achieved the original vision? What has the funding enabled you to do.
J1c | Number crunching: events, people involved, volunteer hours, visitor numbers, income | All of these statistics can be fed into the final evaluation report. | Is there anything about the statistics that surprises you?
J2 | Thank you's, Celebration and what next…
J2a | Thank the funders, volunteers and all involved | Follow up with thank you letters to the funders to say what a difference the funding made. Thank all your volunteers and anyone else involved.
J2b | Celebrate | You have come a long way - enjoy what you and others have achieved.
J2c | Keep going! | Now you have a fixed building, new facilities, community engagement projects, what will you do next? | Do not lose all of that expertise, good will, experience. Think about what you and the wider community might want to do next.